## User Stories
USER ID | USER STORY | PRIORITY | RISK | STORY POINTS
1 | As an athlete, I want to enter weight and height information, so that I can use that information to track and calculate other health information. | Must Do | Low | 3
2 | As an athlete, I want the application to track my weight, so that I can see my improvements. | Must Do | Low | 5
3 | As an athlete, I want to set a target weight, so that I have a weight goal to reach. | Should Do | Low | 1
4 | As an athlete, I want the application to calculate how many pounds per week I should lose, so that I can see if I'm on track with my weight goals. | Could Do | Moderate | 2
5 | As an athlete, I want to enter exercise that I do, so that I can track my activity. | Must Do | High | 8
6 | As an athlete, I want the application to calculate the amount of calories burned in a workout based on the activity and my body size, so that I know the results of my workout. | Could Do | Low | 5
7 | As an athlete, I want the application to notify me if I am not exercising frequently enough, so that I stay in shape. | Should Do | Moderate | 3
8 | As an athlete, I want to be able to enter what I eat for each meal, so that I can track my nutrition. | Must Do | Moderate | 5
9 | As an athlete, I want to enter the calories for the food I eat, so that I know how much I am consuming. | Should Do | Moderate | 2
10 | As an athlete, I want the application to calculate a suggested amount of calories for each meal based on my height and weight, so I can adjust my diet accordingly. | Could Do | Low | 3
11 | As an athlete, I want the application to notify me if I am not meeting my suggested calorie intake, so that I am following my diet accurately. | Could Do | Moderate | 2
12 | As an athlete, I want to enter the amount of water I consume, so that I can track my hydration. | Should Do | Moderate | 3
13 | As an athlete, I want the application to calculate a suggested amount of water that I should consume based on my height and weight, so that I am accurately hydrating. | Could Do | High | 2
14 | As an athlete, I want the application to notify me to remind me to drink water, so that I am constantly hydrating. | Could Do | Moderate | 3
15 | As an athlete, I want to enter fitness goals, so that I have a goal to obtain. | Must Do | Moderate | 2
16 | As an athlete, I want to enter dietary goals, so that I have a goal to obtain. | Must Do | Moderate | 2
17 | As an athlete, I want the application to notify me if I am not meeting my fitness goals, so that I can stay on track to meeting my goals. | Should Do | Moderate | 3
18 | As an athlete, I want the application to notify me if I am not meeting my dietary goals, so that I can stay on track to meeting my goals. | Should Do | Moderate | 3
19 | As an athlete, I want to link a coach to my account, so they can track my progress | Must Do | High | 8
20 | As a coach, I want to see the height and weight information of my athletes, so that I can adjust their trainings and diets appropriately | Must Do | Moderate | 5
21 | As a coach, I want to see the amount of exericse that my athletes are completing, so that I can see how much they are exercising | Must Do | Moderate | 5
22 | As a coach, I want to see what my athletes are eating, so that I can determine if their diet is appropriate for their training | Must Do | Moderate | 5
23 | As a coach, I want to see how much water my athletes are drinking, so that I can make sure they are hydrating appropriately | Could Do | Moderate | 5
24 | As a coach, I want to see the fitness goals of my atheletes, so that I can adjust their trainings to meet their goals | Should Do | Low | 3
25 | As a coach, I want to see the dietary goals of my athletes, so that I can adjust their diet to meet their goals | Should Do | Low | 3

## Project-Gantt
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Company Name | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Project Lead | Project Start: |  | 2020-03-04
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2020-03-02 | [6 empty] | 2020-03-09 | [6 empty] | 2020-03-16 | [6 empty] | 2020-03-23 | [6 empty] | 2020-03-30 | [6 empty] | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-03-02 to 2020-04-26
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-03-02 to 2020-04-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1 Title
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Task 1 | Name | 50% | 2020-03-04 | 2020-03-07 | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Task 2 |  | 60% | 2020-03-07 | 2020-03-09 | 3
| Task 3 |  | 50% | 2020-03-09 | 2020-03-13 | 5
| Task 4 |  | 25% | 2020-03-13 | 2020-03-18 | 6
| Task 5 |  |  | 2020-03-08 | 2020-03-10 | 3
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Phase 2 Title
| Task 1 |  | 50% | 2020-03-09 | 2020-03-13 | 5
| Task 2 |  | 50% | 2020-03-11 | 2020-03-16 | 6
| Task 3 |  |  | 2020-03-16 | 2020-03-19 | 4
| Task 4 |  |  | 2020-03-16 | 2020-03-18 | 3
| Task 5 |  |  | 2020-03-16 | 2020-03-19 | 4
Sample phase title block | Phase 3 Title
| Task 1 |  |  | 2020-03-19 | 2020-03-24 | 6
| Task 2 |  |  | 2020-03-25 | 2020-03-29 | 5
| Task 3 |  |  | 2020-03-30 | 2020-04-04 | 6
| Task 4 |  |  | 2020-04-05 | 2020-04-09 | 5
| Task 5 |  |  | 2020-03-30 | 2020-04-03 | 5
Sample phase title block | Phase 4 Title
| Task 1 |  |  | date | date | #VALUE!
| Task 2 |  |  | date | date | #VALUE!
| Task 3 |  |  | date | date | #VALUE!
| Task 4 |  |  | date | date | #VALUE!
| Task 5 |  |  | date | date | #VALUE!
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## Agile-Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Company Name | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Project Lead |  | Project Start Date: |  | 2018-07-07
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  | July | [27 empty] | August
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2018-07-07 to 2018-08-31
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Title 1
| Task 1 | Goal | Name | 25% | 2020-03-04 | 3
| Task 2 | Milestone |  |  | 2020-03-09 | 1
| Task 3 | Low Risk |  | 50% | 2020-03-01 | 10
| Task 4 | Milestone |  |  | 2020-03-24 | 1
| Task 5 | Med Risk |  | 10% | 2020-03-10 | 6
Title 2
| Task 1 | High Risk |  | 60% | 2020-03-10 | 13
| Task 2 | On Track |  | 50% | 2020-03-12 | 9
| Task 3 | Low Risk |  | 33% | 2020-03-17 | 11
| Task 4 | Milestone |  |  | 2020-03-19 | 1
| Task 5 |  |  |  | 2020-03-20 | 24
Title 3
| Task 1 | On Track |  |  | 2020-03-19 | 4
| Task 2 | Med Risk |  |  | 2020-03-22 | 14
| Task 3 | On Track |  |  | 2020-04-06 | 6
| Task 4 | Goal |  |  | 2020-04-10 | 3
| Task 5 | Low Risk |  |  | 2020-03-10 | 19
Title 4
| Task 1 |  |  |  | 2020-04-13 | 15
| Task 2 |  |  |  | 2018-07-07 | 5
| Task 3 | Milestone |  |  | 2018-07-25 | 1 | bar: W
Task 4
Task 5
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## Agile_docs
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.

## Project_docs
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.

## Sheet1
USER ID